## Overview
UAIS — Issue Register & 3-Month Backlog
Companion workbook to the UAIS Senior Technical Advisory Report — prepared for Dr. Peter Hu, 8 July 2026 (Confidential)
Tab | What it contains
Issue Register | The 18 major issues with evidence, impact, risk, fix, effort, owner, and priority. Filterable.
Backlog | 22 assignable tickets with description, acceptance criteria, priority, phase, owner, and the issue each addresses.
Roadmap | The same tickets sequenced across Weeks 1–2, Weeks 3–4, Month 2, and Month 3, with the phase goal / definition of done.
Readiness Checklist | The minimum bar before inviting real users, mapped to backlog tickets. Use the Status column to track.
Assumptions & Questions | What could not be verified and the questions the owner should answer before major development continues.
Severity key | Critical = user/data harm now • High = serious near-term risk • Medium = important • Low = minor
Priority key | P0 = do first / blocker • P1 = high • P2 = important but later
How to use | Work top-down: clear all P0 tickets in Weeks 1–2 before starting refactors. Track status in the Readiness Checklist and Backlog.

## Issue Register
ID | Issue title | Area | Severity | Evidence / likely symptom | Why it matters | Risk if ignored | Recommended fix | Effort | Suggested owner | Priority (3-mo)
I-01 | No real database — data lives in mock files, JSON, and in-memory maps | Data / Architecture | Critical | src/data/uais.ts is a 553-line mock; server 'stores' persist to local JSON dirs and serialize writes with per-process new Map() queues (localTeachingOperationWriteQueues); no schema/ORM/migrations; 'external storage' is an optional HTTP adapter possibly unconfigured in prod. | Vercel serverless filesystem is ephemeral and not shared across instances, so accounts, enrollments, gradebooks, and learning records do not persist reliably or consistently. 'Backup'/'restore-drill' endpoints simulate durability. | Silent data loss/corruption once real users are invited; analytics and adaptive features cannot be built on non-persistent data. | Adopt managed Postgres (Vercel Postgres/Neon/Supabase) + thin ORM (Prisma/Drizzle) + migrations, implemented behind the existing storage-contract so pages don't change. Keep schema small. | Large | Senior engineer | Month 1–2
I-02 | Login gate in middleware can be bypassed with two arbitrary cookies | Authentication | Critical | src/proxy.ts: authenticated = Boolean(appSessionUser) ¦¦ trustedTeacherSession ¦¦ appSessionCookiePair. hasUaisAppSessionCookiePair() only checks both cookie NAMES are non-empty — no HMAC verification. Two junk cookies pass; role becomes undefined so role routing is skipped. | The login redirect is the first line of defense; a presence-only check does not authenticate. | Unauthenticated visitors reach protected pages; any page trusting middleware alone could expose data. | Remove the appSessionCookiePair fallback; require a validated signed session (or verified teacher session). Add a regression test. NOTE: API routes verify signed sessions + ownership independently, so today it is mainly a UI-gate/defense-in-depth failure. | Small | Senior engineer | Weeks 1–2
I-03 | Demo credentials hardcoded in source and apparently enabled in production | Auth / Privacy | Critical | uais-app-auth-provider.ts hard-codes Phoebe/12345 (teacher) and Peter/12345 (student). Shared live account is Phoebe/12345 and www.uais.top/login accepts account+password — implying UAIS_APP_ALLOW_PRODUCTION_DEMO_AUTH is on in prod. | Anyone with the shared password acts as a teacher and can see student data; no per-user identity/accountability. | Unauthorized access to student data; a privacy incident (potentially minors / cross-border). | Disable production demo auth; wire a real provider (trusted-account provider or teacher OIDC); issue individual accounts with hashed passwords; rotate secrets. Keep demo accounts local/preview only. | Medium | Senior engineer | Weeks 1–2
I-04 | God-files: single source files up to 8,000+ lines | Code quality | High | teaching-page.tsx 8,153; teaching-course-management-store.ts 7,309; teaching-operations-store.ts 4,926; external-storage-route-service.ts 4,144; api/teaching/operations/route.ts 4,121; learning-page.tsx 3,547. | No developer can hold these files in their head or change them safely; guaranteed merge conflicts; hidden bugs. | Every change is high-risk; velocity collapses; onboarding impractical. | Split incrementally by responsibility (presentation vs logic vs data access); extract components/hooks/services; soft budget ~400 lines/file in review. Start with the two most-changed files. | Large | Senior + junior | Month 2
I-05 | Severe scope sprawl — enterprise 'ceremony' around a tiny product | Architecture / Product | High | ~66k lines TS, 56 API routes, 143 test files, 78 env vars, 38 KB 25-agent AGENTS.md — around 2 mock courses + a chatroom UI + teacher workspace. Endpoints for voice-clone lifecycle audits, restore-drills, retention-readiness, owner-decision packets. | Surface area to secure/test/maintain is many times a POC's need and creates a false impression of production-readiness. | Team maintains scaffolding not product; reviewers can't tell real from aspirational; hidden broken paths. | Declare a 'core POC' scope; quarantine aspirational modules under experimental/ (or delete); shrink env surface; simplify the coordination protocol to the real 1–2 dev team. | Medium | Senior + product owner | Weeks 3–4
I-06 | Two overlapping authentication systems | Auth / Architecture | High | HMAC app-session (uais-app-session.ts) coexists with a teacher OIDC chain (teacher-auth-oidc.ts, teacher-auth-session.ts, teacher-auth-issuer-proof.ts) plus uais_teacher_auth_claims/_signature cookies trusted independently by middleware. | Two ways to become 'a teacher' multiply attack surface and confuse which path is authoritative. | Inconsistent enforcement; a gap in one path undermines the other. | Pick ONE session model (recommend signed app-session); express teacher/admin as a role claim; defer OIDC until an institutional IdP is required. | Medium | Senior engineer | Month 2
I-07 | No admin/operator role; RBAC is only teacher/student | Authorization / Product | Medium | UaisAppRole = 'teacher' ¦ 'student'. No admin/operator role despite the brief needing project operators. | Operators must borrow a teacher account; no least-privilege separation. | Over-privileged accounts; can't safely delegate operations. | Add an admin role and a minimal admin surface (user management, moderation). Keep it small and role-gated. | Small–Medium | Senior engineer | Month 2
I-08 | Business logic entangled with UI in page components | Code quality / Product | High | Multi-thousand-line client components (learning-page.tsx, teaching-page.tsx) mix rendering, state, and workflow/business logic. | Logic inside components isn't reusable or unit-testable; UI edits risk breaking behavior. | Fragility; no clean seam to build adaptive features on. | Extract domain logic into src/lib services and hooks; keep components presentational. Do it file-by-file with the God-file split. | Large | Senior + junior | Month 2–3
I-09 | Testing effort misallocated to release/audit ceremony, not user flows | Testing / QA | High | Of 142 test files most are enterprise-live-evidence-audit, owner-decision-*, production-evidence-gate, release-blocker-diagnosis. Core journeys (login→enroll→learn→chat; teacher CRUD) thinly covered. | A large green test count gives false confidence while the flows users depend on are unprotected. | Regressions in real journeys slip through; maintenance spent on ceremony tests. | Add a focused suite for the five critical journeys; archive/retire ceremony tests that don't map to product behavior; make the focused suite the CI merge gate. | Medium | Junior (senior guidance) | Weeks 3–4 → Month 3
I-10 | No error tracking, structured logging, or uptime monitoring | Observability | High | Only @vercel/analytics present. No Sentry-style tracker or ops logging; 'audit/alerts' endpoints are product-data audits, not telemetry. | Production problems can't be diagnosed quickly; outages are learned of from users. | Slow incident response; silent failures. | Add Sentry (client+server), structured server logs, a generalized /healthz, and an external uptime check with alerting. | Small | DevOps / senior | Weeks 1–2
I-11 | Secrets hygiene: hardcoded dev signing secret and loose key files | Security / Deployment | High | uais-app-session.ts falls back to developmentAppSessionSigningSecret in any non-prod runtime. 'All API Keys.docx' and .env.local (real DeepSeek/DashScope keys) sit in the project folder (git-ignored, but risky). 78 env vars widen blast radius. | A known default secret can forge sessions in preview/staging; loose key files invite leaks. | Session forgery outside production; credential leakage. | Require an explicit secret in every deployed env (fail closed); move key material to env vars / a password manager; remove 'All API Keys.docx'; rotate keys. | Small | DevOps / owner | Weeks 1–2
I-12 | No staging/preview separation — production is the only environment | Deployment | High | Single Vercel project; .env.local local + production live uais.top; no documented staging; vercel.json minimal. | Every change is validated against production; no safe place to test migrations or risky features. | Bad deploys reach real users; destructive migrations run against live data. | Use Vercel Preview per PR plus a dedicated staging env with its own DB and secrets; document the promotion flow. | Small–Medium | DevOps | Weeks 3–4
I-13 | File/JSON persistence and per-process queues don't scale beyond one instance | Performance / Scalability | High | Writes serialized with in-process Maps over local JSON dirs while Vercel runs multiple isolated instances that can't see each other's queues/files. | Concurrent writes on different instances race and lose updates. | Corrupted teacher operations and lost gradebook/roster changes under real concurrent use. | Resolve with I-01: a managed DB with transactions. Until then treat writes as best-effort demo only and say so. | Large | Senior engineer | Month 2
I-14 | Large client bundles from huge client components | Performance / UX | Medium | 3,500–8,150-line page components ship heavy client JS and hydrate heavily. | Slow first load, especially on classroom Wi-Fi and mobile. | Teachers/students perceive the POC as sluggish and unreliable. | Move logic to Server Components, code-split and lazy-load heavy panels; measure with Lighthouse before/after. | Medium | Junior + senior | Month 3
I-15 | Adaptive learning is aspirational, not wired to real data | AI / Adaptive readiness | High | LangGraph runtime + provider clients (DeepSeek, Qwen) exist and events are xAPI-shaped, but no persistent learner profile → recommendation → feedback loop; adaptive module is a 'future' file; LRS may be unconfigured. | Adaptivity is the differentiator yet has no data foundation; prompt-only logic is not adaptivity. | Recommendations on non-persistent data are non-reproducible and untrustworthy. | Persist learner_profiles + learning_events in the DB; a small deterministic recommendation service reads them; LLM for generation only, not system-of-record; log all AI I/O for evaluation. | Large | Senior engineer | Month 3
I-16 | API surface undocumented and validation uneven | API / Backend | Medium | 56 route files, no API reference. Some validate carefully (operations route access-denied enum); many ad hoc; nearly all force-dynamic. | New engineers can't discover contracts; inconsistent validation creates reliability/security gaps. | Misuse, inconsistent errors, holes in weaker routes. | For core routes only: a shared zod validator, one error shape, and a short API.md. Park non-core routes. | Medium | Senior engineer | Month 2
I-17 | Documentation not matched to a small team; onboarding runbook missing | Docs / Workflow | Medium | AGENTS.md is a 38 KB 25-agent nightly-meeting protocol. README is reasonable but no from-zero setup, coding standards, or branching/PR/deploy/rollback runbook for a human junior. | The coordination doc governs imaginary 25-agent parallelism, not the 1–2 person reality; a new human dev lacks a practical runbook. | Wasted effort following ceremony; slow, unsafe onboarding. | Write a short CONTRIBUTING.md (setup/run/test/branch/PR/deploy/rollback) and a one-page architecture map; shrink AGENTS.md to the real team. | Small | Senior / junior | Weeks 3–4
I-18 | No simple rollback runbook; build artifacts committed | Deployment / QA | Medium | Rollback is 'redeploy a previous Vercel build,' undocumented; elaborate release-gate scripts but no 2-minute human rollback. tsconfig.tsbuildinfo committed to git. | During an incident the team needs a fast, boring rollback — not a 38 KB protocol. | Prolonged outages; panic changes. | Document 'how to roll back in Vercel' + a pre-deploy checklist; remove build artifacts from version control; ensure npm run build is clean in CI. | Small | DevOps | Weeks 1–2

## Backlog
ID | Title | Description | Acceptance criteria | Priority | Phase | Suggested owner | Addresses
B-01 | Remove middleware presence-only auth bypass | Delete the appSessionCookiePair fallback in src/proxy.ts and require a verified signed session (or verified teacher session) to treat a request as authenticated. | Forged/junk cookie pair is redirected to /login; valid signed session still works; regression test added and passing in CI. | P0 | Weeks 1–2 | Senior engineer | I-02
B-02 | Disable production demo auth and gate real-user access | Ensure UAIS_APP_ALLOW_PRODUCTION_DEMO_AUTH is off in production; demo accounts work only in local/preview. Add a startup check that fails closed in production if only demo auth is configured. | In production, Phoebe/12345 no longer grants access; local/preview unaffected; documented in CONTRIBUTING. | P0 | Weeks 1–2 | Senior engineer | I-03
B-03 | Enforce required session signing secret in deployed envs | resolveUaisAppSessionSigningSecret returns no usable value in any deployed environment unless UAIS_APP_SESSION_SIGNING_SECRET is set; remove reliance on the hardcoded dev default outside local dev. | App refuses to issue/accept sessions without an explicit secret in preview/staging/prod; local dev works; test covers the fail-closed path. | P0 | Weeks 1–2 | DevOps / senior | I-11
B-04 | Rotate secrets and remove key files from the project folder | Rotate DeepSeek/DashScope and session secrets; move all key material into Vercel env vars / a password manager; delete 'All API Keys.docx' from the working directory. | No secret files remain in the repo folder; keys rotated; access still works via env vars. | P0 | Weeks 1–2 | DevOps / owner | I-11
B-05 | Add error tracking and uptime monitoring | Integrate Sentry (client + server), add a generalized /healthz endpoint, and configure an external uptime check with alerting to the owner. | Errors appear in Sentry with source maps; uptime alert fires on a forced outage; /healthz returns 200. | P0 | Weeks 1–2 | DevOps / senior | I-10
B-06 | Write the rollback runbook and pre-deploy checklist | One page: how to roll back a Vercel deployment in under 2 minutes, plus a pre-deploy checklist (build green, migrations reviewed, secrets set). | Runbook committed under docs/; a test rollback is performed and timed once. | P1 | Weeks 1–2 | DevOps | I-18
B-07 | Declare core POC scope and quarantine experimental modules | Document the core scope (courses, learning, chatroom, teaching, auth). Move aspirational modules (voice-clone, ppt-narration, enterprise-audit/evidence) under an experimental/ boundary or remove them. | A SCOPE.md lists in-scope vs parked modules; parked code is clearly separated and excluded from the core test gate. | P1 | Weeks 3–4 | Senior + product owner | I-05
B-08 | Author CONTRIBUTING.md and a one-page architecture map | Setup-from-zero, run/test/lint, branch naming, PR process, deploy, rollback; plus a diagram of routes, auth, data, and AI. | A new developer can clone and run the app using only CONTRIBUTING.md; architecture map reviewed by owner. | P1 | Weeks 3–4 | Senior / junior | I-17
B-09 | Stand up staging and per-PR preview environments | Create a staging Vercel environment with its own database and secrets; enable Preview deploys per pull request. | PRs get a preview URL; staging is reachable and isolated from production data. | P1 | Weeks 3–4 | DevOps | I-12
B-10 | Design the minimal relational schema | Design tables for users, courses, lessons, enrollments, assessments, submissions, learning_events, learner_profiles. Review for integrity and privacy. | Reviewed ERD/migration draft; naming and foreign keys agreed; no student PII stored beyond what is needed. | P1 | Weeks 3–4 | Senior engineer | I-01
B-11 | Introduce managed Postgres + ORM + migrations | Provision managed Postgres; add Prisma or Drizzle; implement the schema behind the existing storage-contract abstraction so pages are unchanged. | Migrations run in CI and staging; a seed script creates demo data; storage-contract adapter reads/writes the DB. | P1 | Month 2 | Senior engineer | I-01
B-12 | Migrate core entities off file/JSON storage | Replace file/JSON persistence for users, enrollments, and teacher operations with DB-backed adapters using expand/contract; keep mock path until parity is proven. | Reads/writes go to Postgres; concurrent writes no longer race; old file path removed after parity sign-off. | P1 | Month 2 | Senior engineer | I-13
B-13 | Consolidate to one session model and add admin role | Collapse the teacher OIDC chain into the signed app-session with a role claim; add an admin role and a minimal admin surface. | One session cookie governs access; roles student/teacher/admin enforced in middleware and API; OIDC parked. | P1 | Month 2 | Senior engineer | I-06 / I-07
B-14 | Split the two most-changed God-files | Refactor teaching-page.tsx and learning-page.tsx into presentational components + extracted hooks/services; no behavior change. | Each new file is well under the agreed budget; UI unchanged; existing tests green; critical-flow tests added. | P2 | Month 2 | Senior + junior | I-04 / I-08
B-15 | Standardize API validation and error shape for core routes | Add a shared zod-based validator and one error response shape to the core routes; write a short API.md for them. | Core routes reject invalid input consistently; API.md documents each; contract tests pass. | P2 | Month 2 | Senior engineer | I-16
B-16 | Build the critical-flow test suite | Cover login (incl. forged-cookie rejection), enrollment, learning playback, chatroom send/export, and teacher course CRUD. | Five journeys covered end-to-end; suite runs in CI as the merge gate; ceremony tests archived. | P1 | Weeks 3–4 → Month 3 | Junior (senior guidance) | I-09
B-17 | Persist learner profiles and learning events | Write xAPI-shaped events and a learner_profile row per student to the database on each meaningful learning action. | Events and profiles are queryable in Postgres; a simple report shows per-student progress. | P2 | Month 3 | Senior engineer | I-15
B-18 | Ship a minimal deterministic recommendation service | A small service reads learner_profiles + learning_events and returns the next recommended unit; the LLM is used only for generation, with all I/O logged. | Given seeded data, the service returns a stable next-step; AI inputs/outputs are logged for evaluation. | P2 | Month 3 | Senior engineer | I-15
B-19 | Performance pass on bundles and queries | Move logic server-side, code-split heavy panels, add DB indexes for hot queries; measure with Lighthouse and query timings. | Largest route's client JS reduced measurably; key pages score materially higher on Lighthouse; no N+1 on hot paths. | P2 | Month 3 | Junior + senior | I-14
B-20 | Accessibility and UX reliability pass | Audit forms, loading and error states, keyboard navigation, and contrast on the five core screens; fix the top issues. | Core screens have visible loading/error states, labelled forms, and pass an automated a11y check for critical violations. | P2 | Month 3 | Junior + designer | I-14
B-21 | Shrink the environment-variable surface | Remove or park env vars tied to quarantined modules; document the remaining core vars in .env.local.example. | Core env list is short and documented; app boots with only the core vars set in staging. | P2 | Month 2 | Senior engineer | I-05
B-22 | Privacy & data-handling baseline | Document what student data is collected, where it lives, retention, and deletion; confirm consent copy on the login/terms/privacy pages matches reality. | A short data-handling note exists; privacy/terms pages match actual processing; a data-deletion path is defined. | P1 | Month 2 | Senior + product owner | I-03

## Roadmap
Phase | Phase goal / theme | Ticket | Priority | Definition of done (per ticket)
Weeks 1–2 | Stabilization & risk reduction | B-01 Remove auth bypass | P0 | A forged cookie pair no longer reaches protected pages (proven by test).
Weeks 1–2 | Stabilization & risk reduction | B-02 Disable production demo auth | P0 | Phoebe/12345 no longer grants access in production.
Weeks 1–2 | Stabilization & risk reduction | B-03 Require session signing secret | P0 | App fails closed without an explicit secret in deployed envs.
Weeks 1–2 | Stabilization & risk reduction | B-04 Rotate secrets; remove key files | P0 | No secret files in repo folder; keys rotated.
Weeks 1–2 | Stabilization & risk reduction | B-05 Error tracking + uptime | P0 | Errors/outages surface within minutes.
Weeks 1–2 | Stabilization & risk reduction | B-06 Rollback runbook | P1 | Team can roll back a bad deploy in under 2 minutes.
Weeks 3–4 | Architecture cleanup & documentation | B-07 Declare core scope; quarantine | P1 | In-scope vs parked modules documented and separated.
Weeks 3–4 | Architecture cleanup & documentation | B-08 CONTRIBUTING + architecture map | P1 | A new dev can set up and run UAIS from the docs alone.
Weeks 3–4 | Architecture cleanup & documentation | B-09 Staging + preview envs | P1 | PRs get preview URLs; staging isolated from prod.
Weeks 3–4 | Architecture cleanup & documentation | B-10 Design schema | P1 | A reviewed schema/ERD is ready to implement.
Weeks 3–4 | Architecture cleanup & documentation | B-16 Start critical-flow tests | P1 | Login and enrollment covered end-to-end.
Month 2 | Core refactoring & feature foundation | B-11 Postgres + ORM + migrations | P1 | Core data stored in Postgres; survives redeploys.
Month 2 | Core refactoring & feature foundation | B-12 Migrate core entities | P1 | Concurrent writes no longer race.
Month 2 | Core refactoring & feature foundation | B-13 One session model + admin role | P1 | Roles student/teacher/admin enforced.
Month 2 | Core refactoring & feature foundation | B-14 Split two God-files | P2 | Refactored files under budget; tests green.
Month 2 | Core refactoring & feature foundation | B-15 API validation + API.md | P2 | Core routes validate consistently and are documented.
Month 2 | Core refactoring & feature foundation | B-22 Privacy baseline | P1 | Data-handling documented; privacy copy matches reality.
Month 3 | Hardening, testing & controlled expansion | B-16 Finish critical-flow tests (CI gate) | P1 | CI blocks merges that break a critical journey.
Month 3 | Hardening, testing & controlled expansion | B-17 Persist learner profiles/events | P2 | Per-student progress is queryable.
Month 3 | Hardening, testing & controlled expansion | B-18 Recommendation service | P2 | A reproducible next-step from stored data.
Month 3 | Hardening, testing & controlled expansion | B-19/B-20 Performance + a11y pass | P2 | Core pages load acceptably and pass a11y checks.
Month 3 | Hardening, testing & controlled expansion | B-21 Shrink env surface | P2 | App boots with only documented core vars.

## Readiness Checklist
Area | Checklist item (must be true before real users) | Backlog ref | Status
Security | Middleware requires a verified signed session (no presence-only bypass). | B-01 | ☐ Open
Security | Production demo auth disabled; individual accounts with hashed passwords. | B-02 | ☐ Open
Security | Session signing secret required in every deployed environment (fail closed). | B-03 | ☐ Open
Security | Secrets in env vars / a manager; no key files in the repo folder; keys rotated. | B-04 | ☐ Open
Security | Roles student/teacher/admin enforced in middleware and API routes. | B-13 | ☐ Open
Data | Core data in a managed database with migrations; redeploy- and concurrency-safe. | B-11 / B-12 | ☐ Open
Data | A real, tested backup and restore path (not a simulated 'restore-drill'). | B-11 | ☐ Open
Data | Documented data-handling: what is collected, where it lives, retention, deletion. | B-22 | ☐ Open
Deployment | Separate Preview / Staging / Production with isolated data and secrets. | B-09 | ☐ Open
Deployment | Clean, reproducible npm run build in CI; build artifacts out of version control. | B-18* | ☐ Open
Deployment | Documented, timed rollback procedure. | B-06 | ☐ Open
Testing | Automated tests for the five critical journeys, running as the CI merge gate. | B-16 | ☐ Open
Monitoring | Error tracking (Sentry) and an external uptime check with alerting. | B-05 | ☐ Open
Monitoring | A health endpoint and basic structured server logs. | B-05 | ☐ Open
Documentation | CONTRIBUTING.md and a one-page architecture map. | B-08 | ☐ Open
Documentation | A short API.md for core routes; env vars documented in .env.local.example. | B-15 / B-21 | ☐ Open
User experience | Every core screen has visible loading and error states and labelled forms. | B-20 | ☐ Open
User experience | Core pages are responsive and load acceptably on classroom Wi-Fi and mobile. | B-19 | ☐ Open
Privacy | Login/terms/privacy copy matches actual processing; consent is meaningful. | B-22 | ☐ Open
* Build-clean-in-CI is verified as part of the deploy/CI setup alongside B-18's evaluation logging work.

## Assumptions & Questions
Type | Item | Detail / basis | Action / who answers
Assumption | Production demo auth is enabled | Inferred from the owner distributing Phoebe/12345 and the live login accepting account+password. NOT confirmed by an active login (the live site was not exploited). | Confirm whether demo auth is on in prod; disable it (B-02).
Assumption | Hosting is Vercel serverless | Inferred from .vercel, vercel.json, @vercel/analytics. Regions and whether external storage is configured in prod not confirmed. | Confirm hosting details and any live storage backend.
Assumption | File/JSON stores are the active persistence in prod | If a real external storage service is connected, severity of I-01/I-13 drops. This is the single most important thing to confirm. | Confirm the production persistence path (biggest unknown).
Assumption | Build/test/lint not run in this advisory | Read-only review; build health assumed from config, not observed. | Run npm run build/test/lint and record results.
Open question | Real database connected in production? | Is any real DB/external storage connected today, or is all persistence mock/file-based? | Owner to answer before major dev continues.
Open question | Users and minors | How many real users, by when, and will any be minors? Drives privacy/consent/security bar. | Owner to answer.
Open question | Template vs product | Is uais.top a reusable template or a single live product? Changes how much to invest and delete. | Owner to answer.
Open question | Approved AI providers | Which providers (DeepSeek/Qwen) are approved for production; cost/rate limits? | Owner to answer.
Open question | Compliance/residency | China PIPL, and GDPR for any international students — what applies? | Owner to answer.
Open question | 25-agent workflow | Keep and formalize, or retire as an experiment? It adds significant overhead today. | Owner to decide.